## Sheet1
Pre-Start | 000 - 200
During Beta | 201 - 400
After Beta | 500 - 600
Sales | 700 - 800
Department | Order | Tasks | Owner | Doc | path |  | Prior | -6 weeks | -5 weeks | -4 weeks | -3 weeks | -2 weeks | -1 week | 1 week | 2 weeks | 3 weeks | 4 weeks | 5 weeks | 6 weeks
Beta Owner | 0 | Non-Disclosure Agreement |  | x |  | Sent
Beta Owner | 0 | Non-Disclosure Agreement Letter |  | x |  | Sent
Beta Owner | 5 | Letter and schedule
Beta Owner | 10 | Participation Agreement
Beta Owner | 11 | Obtain Beta proposal signed |  |  |  |  | X
Beta Owner | 15 | Prospect Survey
Marketing | 51 | Welcome Word |  | x |  | Web
Marketing | 55 | FAQ |  | x |  | Web
Marketing | 60 | Schedule |  | x |  | Web
Marketing | 63 | provide access to SPOC in back end of website |  | x |  | Web |  |  |  |  | X
Marketing | 65 | Participant's Logo |  | x |  | Web
Marketing | 70 | SPOC Names |  | x |  | Web
Marketing | 71 | SPOCs Contact Info |  | x |  | Web
Marketing | 72 | Location |  | x |  | Web
Marketing | 80 | Lexicon |  | x |  | Web
Marketing | 85 | update to website - we are currently in Beta testing |  | x |  | Web
Marketing | 90 | Tester identification |  | x |  | Web
Marketing | 100 | Post Questions Week 01 to Beta Partner Success Portal |  | x |  | Web
Marketing | 100 | Post Questions Week 02 to Beta Partner Success Portal |  | x |  | Web
Marketing | 100 | Post Questions Week 03 to Beta Partner Success Portal |  | x |  | Web
Marketing | 100 | Post Questions Week 04 to Beta Partner Success Portal |  | x |  | Web
Marketing | 200 | Key Performance Indicators |  | x |  | Web
Beta Owner | 210 | 3-step feedback from users - after 2 weeks | [12 empty] | X
Beta Owner | 211 | 3-step feedback from users - at end week 1 | [11 empty] | X | X | X | X
Beta Owner | 211 | 3-step feedback from users - at end of each week period | [11 empty] | X | X | X | X
Beta Owner | 211 | 3-step feedback from users - at end of each week period | [11 empty] | X | X | X | X
Beta Owner | 211 | 3-step feedback from users - at end of each week period | [11 empty] | X | X | X | X
Beta Owner | 225 | Obtain answers to Questions Week 01
Marketing | 225 | Post Answers to Questions from Week 01 |  | x |  | Web
Beta Owner | 226 | Obtain answers to Questions Week 02
Marketing | 226 | Post Answers to Questions from Week 02 |  | x |  | Web
Beta Owner | 227 | Obtain answers to Questions Week 03
Marketing | 227 | Post Answers to Questions from Week 03 |  | x |  | Web
Beta Owner | 228 | Obtain answers to Questions Week 04
Marketing | 228 | Post Answers to Questions from Week 04 |  | x |  | Web
Beta Owner | 229 | Obtain answers to Questions Week 05
Marketing | 229 | Post Answers to Questions from Week 05 |  | x |  | Web
Beta Owner | 230 | Obtain answers to Questions Week 06
Marketing | 231 | Post Answers to Questions from Week 06 |  | x |  | Web
Ops | 540 | Get Beta amulets returned to EERS | [15 empty] | X
Marketing | 550 | post 4 weeks. Confirm VOC stories, feedback, testimonials | [15 empty] | X
Team | 575 | Post Mortem
Marketing | 580 | press releases?
Sales | 750 | Sales - Contract
Beta Owner |  | collect testimonials and onsite photography | [14 empty] | X
Beta Owner |  | fill out prospect preliminary survey |  |  |  |  | X
Beta Owner |  | Net promoter score survey - (change over time?) 4 weeks out | [11 empty] | X | X | X | X
Beta Owner |  | post install Tech Support for feedback form | [9 empty] | X
Beta Owner |  | pre install "baseline - A priory" survey with participants | [9 empty] | X
Customer Support |  | 3-step onboarding success program - 0 day - onboarding day | [10 empty] | X
Customer Support |  | 3-step onboarding success program - 1 week out lunch and learn | [10 empty] | X
Customer Support |  | 3-step onboarding success program - 3 weeks out - email for management to share, invite to lunch and learn | [8 empty] | X
Customer Support |  | end of day of onboarding feedback | [10 empty] | X
Customer Support |  | identify super users, champions & possitive players for the team. | [7 empty] | X
Marketing |  | upload Customer Support docs | [8 empty] | X
Ops |  | onsite install of data hubs | [9 empty] | X
Ops |  | ship data hubs to site | [9 empty] | X
Ops |  | validate data hub is properly functioning | [9 empty] | X
product manager |  | paper based data migration
R&D |  | program data hubs | [7 empty] | X
R&D |  | R&D site visit during Beta (observation) | [12 empty] | X
Sales |  | confirm in discount proposal for Beta site
Sales |  | cost of Sales doc |  |  |  |  | X
Sales |  | expence report for training, on site travel, etc. | [15 empty] | X
Sales |  | follow up for Sales contract | [15 empty] | X
Sales |  | NDA in place |  |  |  |  | X
Sales |  | sign Beta Participation Agreement |  |  |  |  | X
Team |  | analysis of data collected from Beta site data (amount of talk time, battery life, et al) | [16 empty] | X
Team |  | identify single point of contact |  |  |  |  | X
Ops |  | assign amulets on excel sheet (validated at training) | [5 empty] | X
Ops |  | conduct implementation phone call and fill out tech survey | [5 empty] | X?
certification process?
QA onsite technical product testing (reliability)
Note on G8: Microsoft Office User: file folder location
Note on H8: Microsoft Office User: where it will be located or housed for client access